## Project Planner
Project Planner
ACTIVITY | SCHOOL WEEKS
| 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17
Everyone
Project Proposal | bar: SCHOOL WEEKS 7 to SCHOOL WEEKS 8
Slides | bar: SCHOOL WEEKS 7 to SCHOOL WEEKS 8
Consult with teammates | bar: SCHOOL WEEKS 8; SCHOOL WEEKS 10; SCHOOL WEEKS 12; SCHOOL WEEKS 14; SCHOOL WEEKS 16
Final Scratch Integration
Kaede (E-Learning Module)
Homepage | bar: SCHOOL WEEKS 9 to SCHOOL WEEKS 12
Lesson 1 - greeting customer | bar: SCHOOL WEEKS 9 to SCHOOL WEEKS 13
Lesson 2 -taking orders | bar: SCHOOL WEEKS 9 to SCHOOL WEEKS 14
Lesson 3 - handling requests | bar: SCHOOL WEEKS 9 to SCHOOL WEEKS 15
Lesson 4 - manage complains | bar: SCHOOL WEEKS 9 to SCHOOL WEEKS 16
Jin Hui (Quiz)
Homepage | bar: SCHOOL WEEKS 10 to SCHOOL WEEKS 12
Quiz 1 | bar: SCHOOL WEEKS 12 to SCHOOL WEEKS 13
Quiz 2 | bar: SCHOOL WEEKS 13 to SCHOOL WEEKS 14
Quiz 3 | bar: SCHOOL WEEKS 13 to SCHOOL WEEKS 15
Final page | bar: SCHOOL WEEKS 14 to SCHOOL WEEKS 15
Deva (Story-based branching)
Scratch story- based braching (homepage) | bar: SCHOOL WEEKS 8 to SCHOOL WEEKS 9
Story 1 | bar: SCHOOL WEEKS 9 to SCHOOL WEEKS 11
Story 2 | bar: SCHOOL WEEKS 11 to SCHOOL WEEKS 13
Story 3 | bar: SCHOOL WEEKS 12 to SCHOOL WEEKS 14
Story 4 | bar: SCHOOL WEEKS 13 to SCHOOL WEEKS 15
Thank you page | bar: SCHOOL WEEKS 14 to SCHOOL WEEKS 16
Kimlin (Introduction)
SCRATCH: Main menu | bar: SCHOOL WEEKS 9 to SCHOOL WEEKS 10
SCRATCH: Introduction | bar: SCHOOL WEEKS 10 to SCHOOL WEEKS 12
SCRATCH: Home page | bar: SCHOOL WEEKS 12 to SCHOOL WEEKS 14
SCRATCH: Linking the pages | bar: SCHOOL WEEKS 14 to SCHOOL WEEKS 16
Venise (Game)
SCRATCH: Game menu | bar: SCHOOL WEEKS 9 to SCHOOL WEEKS 10
SCRATCH: Selection pages; Cashier Start Page and Guide: How To Play | bar: SCHOOL WEEKS 10 to SCHOOL WEEKS 13
SCRATCH: Controls Page, Settings Page and Cashier Gameplay | bar: SCHOOL WEEKS 11 to SCHOOL WEEKS 16
SCRATCH: Fixes | bar: SCHOOL WEEKS 9 to SCHOOL WEEKS 17